COMMON  /  TEAM WORKSPACE  /  1

# Common build workspace

# Common ETHOnline 2026 Build Plan

Shared spending memory for AI agents

Build a working system where independent agents share a budget, reuse paid results, and learn from earlier spending outcomes. This workspace gives Aditya, Kavish, and the project lead clear ownership, development interfaces, and phase gates so each person can progress independently.

| Property | Plan |
| --- | --- |
| Project status | Planning — task statuses below are not started |
| Team | Aditya · Kavish · Project lead |
| Build window | 10 working days; map relative days to your actual deadline |
| Primary demo | Two agents, one purchase, two completed deliverables |
| Primary sponsor focus | Hedera agentic payments; meaningful live Graph data use |
| Working rule | Agree interfaces first; ship mocks before connecting live services |

## Start here

☐  Confirm the scope and ownership on page 2.

☐  Complete interface agreement on page 3 before parallel implementation.

☐  Prove controlled payment and live indexing paths by day 2.

☐  Use pages 4–6 for phase execution and acceptance gates.

☐  Track tasks and blockers on page 7; prepare the demo using page 8.

## Definition of success

A real paid request runs through the enforced workspace budget. A second agent discovers the indexed purchase, retrieves an authorized usable result, and completes its task. The team can inspect the decision record, receipt, result, and measured spending. Recovery never blindly repeats a payment.

COMMON  /  TEAM WORKSPACE  /  2

# Scope and team ownership

| Owner | Accountable for | Owned paths |
| --- | --- | --- |
| Aditya | Subgraph, event mappings, live queries, purchase discovery and analytics | subgraph/ packages/graph-client/ docs/graph.md |
| Kavish | Reservation contract, controlled payments, x402 service, HCS and deployment | contracts/ packages/hedera-adapter/ apps/paid-service/ infra/ |
| Project lead | Interfaces, agents, orchestration, storage, frontend, integration and submission | packages/interfaces/ packages/agent-tools/ packages/result-store/ apps/web/ apps/orchestrator/ |

## MVP checklist

☐  Create and fund a workspace; authorize two agents.

☐  Reserve one purchase atomically when agents compete.

☐  Execute a real x402 payment through Blocky402.

☐  Store the result with freshness and capability metadata.

☐  Let the second agent discover and reuse the result through live Graph queries.

☐  Write decision notes to HCS and link them to indexed events.

☐  Show a later decision avoiding a known unsuitable result.

☐  Demonstrate safe unpaid expiry and paid delivery failure.

## Keep outside the MVP

Defer marketplaces, multiple payment networks, streaming payments, general semantic duplicate detection, reputation systems, and elaborate identity integrations. Add polish only after the complete real flow passes.

## Ownership rules

Each component owner supplies its build command, tests, example configuration, and live adapter. Kavish owns deployment infrastructure; he does not own repairing every application. The lead resolves scope and interface conflicts; the person who owns a failing component fixes it.

Shared files such as the root package manifest and interfaces have one merge owner: the project lead. Discuss changes with the relevant component owner before editing their paths.

COMMON  /  TEAM WORKSPACE  /  3

# Phase 0 agree the interfaces

WHEN  First half-day     OWNER  Project lead with both teammates

Freeze the smallest shared contract that allows all three workstreams to compile and run independently. Aditya and Kavish review event and adapter definitions before implementation starts.

| Agreement | Required decision |
| --- | --- |
| Identifiers | workspaceId, operationId, purchaseKey and decisionId have stable formats. |
| Money | Integer token units serialized as strings; include token identity and decimals. |
| Purchase key | Provider, resource, normalized parameters, workspace and freshness bucket. |
| Operation states | Reserved, payment pending, paid, delivered, delivery failed, released and expired; define transitions. |
| Decision fields | Buy, reuse, wait or reject; alternative, reason, outcome, result reference and evidence IDs. |
| Result metadata | Freshness expiry, capability tags, usable flag and failure reason; private content stays in authorized storage. |
| Errors and reads | Typed errors plus indexed block or synchronization status. Define empty results and pagination. |

## Component interfaces

SpendingAdapter — reserve, executePayment, getOperation, release, recordDecision. Kavish supplies a real implementation; the lead supplies fixtures.

MemoryReader — findPurchases, getDecisionHistory, getWorkspaceStats. Aditya supplies the Graph implementation with the same response shapes as the fixtures.

ResultStore — put and get an authorized result reference. The lead owns storage and retrieval checks.

## Authority and consistency

Graph supports discovery and history. Contract checks and verified payment state decide whether spending is permitted. A delayed index must never authorize a second purchase. Decisions and payment states remain separate: reuse and wait decisions do not create payments.

☐  Commit versioned types, event ABI and representative JSON fixtures.

☐  All three components compile against the shared interfaces.

☐  Agree how reuse decisions become indexable events, including who may submit them.

COMMON  /  TEAM WORKSPACE  /  4

# Phases 1 and 2 build in parallel

## Phase 1 independent foundations

WHEN  Days 1–2     GATE  Mock demo plus real feasibility evidence

| Owner | Deliverables |
| --- | --- |
| Aditya | Define Workspace, Purchase and Decision entities. Build mappings from sample events and a fixture-backed query client. Validate the actual live indexing and deployment path. |
| Kavish | Implement reservation and authorization foundation. Stand up the gated service and prove a real Blocky402 request. Validate that agents cannot bypass the budget via the signer. Start HCS recording. |
| Project lead | Build the frontend, two agent workflows, result storage and orchestrator against mocks. Create the shared fixture suite and run the full simulated demo. |

Shared fixtures: successful purchase, reusable result, conflicting reservation, insufficient budget, stale result, unusable result, unknown settlement, and paid delivery failure.

☐  Full demo runs with mocks and is clearly labeled as simulated.

☐  Payment proof includes a real receipt and the proposed enforced funding path.

☐  Live Graph deployment feasibility is demonstrated, not assumed.

## Phase 2 real components

WHEN  Days 3–4     GATE  Independently runnable live components

| Owner | Deliverables |
| --- | --- |
| Aditya | Live purchase and outcome queries; decision history; counters; synchronization metadata; deployed endpoint and example queries. |
| Kavish | Funding, atomic reservations, expiry rules, settlement reconciliation, indexed events, HCS notes and deployment scripts. |
| Project lead | Persistent workflow operations, agent tools, freshness and capability checks, wait/resume behavior, deliverables and a comparable baseline run. |

☐  Each component has documented setup, environment variables and a smoke test.

☐  Unknown settlement cannot expire into another payment.

☐  Mocks and live implementations return compatible responses.

COMMON  /  TEAM WORKSPACE  /  5

# Phase 3 integrate the real workflow

WHEN  Days 5–6     OWNER  Project lead coordinates component owners

Connect one complete flow before adding more scenarios. Swap one adapter at a time so any failure has a clear boundary and owner.

| Step | Connection | Pass evidence |
| --- | --- | --- |
| 1 | Orchestrator → reservation | Authorized reserve succeeds and reduces available budget. |
| 2 | Reservation → payment → storage | Real receipt and stored result share the operation ID. |
| 3 | Decision → event and HCS | Both records use the same decision ID and relevant receipt references. |
| 4 | Contract event → Graph | Live query returns the purchase, outcome and result reference. |
| 5 | Agent B → indexed memory → result | Agent retrieves authorized usable data without a new purchase. |
| 6 | Agents → deliverables → dashboard | Both outputs complete; displayed totals match operations. |

## Write recovery

Persist a pending write before sending it. Contract and HCS writes are not atomic. Retry an HCS note independently of payment execution. Use stable IDs and reconciliation to avoid duplicate records and duplicate counter increments. An HCS timestamp establishes ordering; it does not prove the explanation is true.

## Read recovery

When a purchase is pending or not yet indexed, keep the workflow in a visible waiting state and check authoritative operation status. Do not treat an empty Graph result as permission to buy. Always go through the contract reservation check.

## Integration ownership

Aditya fixes mappings, query responses and indexing behavior. Kavish fixes contract, payment, HCS and infrastructure behavior. The lead fixes orchestration, result access and UI behavior. Track interface changes explicitly instead of patching around inconsistent fields.

☐  A clean workspace completes one real purchase and two deliverables.

☐  The live Graph record and HCS note can be opened from the evidence trail.

☐  Restarting the orchestrator does not lose the operation or repeat payment.

COMMON  /  TEAM WORKSPACE  /  6

# Phase 4 verify decisions and recovery

WHEN  Days 7–8     GATE  Repeatable tests and honest measurements

| Scenario | Expected behavior | Owner |
| --- | --- | --- |
| Concurrent purchase | Only one competing reservation succeeds. | Kavish |
| Repeated execution | Stable operation ID prevents another payment. | Kavish + lead |
| Index delay | Contract still prevents duplicate spending. | Aditya + lead |
| Stale result | Reject reuse and follow controlled acquisition. | Lead |
| Unsuitable prior result | Use capability outcome to choose appropriately. | Lead |
| Crash before payment | Safely release or expire unpaid reservation. | Kavish + lead |
| Settlement unknown | Reconcile before retry or budget release. | Kavish |
| Paid delivery failure | Record failure without blind repurchase. | Kavish + lead |
| HCS failure | Retry note independently from payment. | Kavish + lead |
| Policy change | Next spend obeys current contract policy. | Kavish |

## Measurement definitions

Reuse rate = successful reuses ÷ (successful reuses + successful new acquisitions), per distinct resource need. Exclude failed and denied requests from this denominator and report them separately. Show N/A when the denominator is zero.

Estimated avoided purchase cost uses observed quotes for resources actually reused. Report actual purchase spend and coordination fees separately. Claim net savings only when the relevant costs are measured.

Use the same task, inputs and completion criteria with Common enabled and disabled. Record runtime and deliverable quality so cheaper execution is not confused with incomplete work.

☐  All money-safety cases pass with evidence linked to the relevant task.

☐  Successful reuse means the result contributed to a completed deliverable.

☐  The benchmark can be rerun from a clean workspace.

COMMON  /  TEAM WORKSPACE  /  7

# Team task and blocker trackers

Use this page as an editable project board. Status values: Not started, In progress, Review, Done, Blocked. Mark Done only when the acceptance evidence exists.

| ID | Task | Owner | Due | Status |
| --- | --- | --- | --- | --- |
| C01 | Types, ABI and fixtures frozen | Lead | Day 1 | Not started |
| G01 | Live indexing feasibility | Aditya | Day 2 | Not started |
| H01 | Controlled real payment proof | Kavish | Day 2 | Not started |
| I01 | Complete mock demo | Lead | Day 2 | Not started |
| G02 | Live query client and mappings | Aditya | Day 4 | Not started |
| H02 | Contract, HCS and recovery | Kavish | Day 4 | Not started |
| I02 | Agents and persistent workflow | Lead | Day 4 | Not started |
| I03 | Real end-to-end flow | Lead | Day 6 | Not started |
| Q01 | Component failure tests | All owners | Day 8 | Not started |
| D01 | Stable deployment | Kavish | Day 9 | Not started |
| S01 | Graph integration evidence | Aditya | Day 9 | Not started |
| S02 | Demo and submission | Lead | Day 10 | Not started |

## Blocker record template

ID: ______   Owner: ______   Raised: ______   Next review: ______
Blocked task: ______________________________________________
Observed failure and evidence: ________________________________
Next action and person needed: _______________________________
Independent work or fixture fallback: __________________________

## Daily working agreement

Hold a 15-minute check-in: what works, what changed, and what needs a decision. Merge small changes daily. Use short branches such as codex/graph-queries and codex/payment-recovery. Do not change interfaces silently. Continue against fixtures while a live dependency is unavailable, but keep the integration failure visible.

If a foundational path fails, the lead makes a scope decision that day with the owner. Do not disguise a mock as a working sponsor integration.

COMMON  /  TEAM WORKSPACE  /  8

# Phase 5 deployment and submission

WHEN  Days 9–10     GATE  Stable demo and complete evidence

| Owner | Final checklist |
| --- | --- |
| Aditya | Final Graph endpoint, example queries, counter verification, and documentation showing how live data changes an agent decision. |
| Kavish | Hosted services, health checks, testnet addresses, receipt evidence, HCS references, configuration and restart instructions. |
| Project lead | Final UI, reproducible demo, benchmark summary, architecture README, video and submission. |

## Demo storyboard

☐  Explain the duplicate-purchase problem and show the shared budget.

☐  Run two independent agents requesting the same dataset.

☐  Show one actual payment and the second agent waiting.

☐  Show reuse and two completed deliverables.

☐  Show a later decision avoiding an unsuitable prior outcome.

☐  Open the live Graph result and HCS evidence; show spend and reuse.

## Release checklist

☐  Freeze features before recording; fix only release-blocking bugs.

☐  Test a clean install using the README and example environment file.

☐  Keep credentials out of the repository and video.

☐  Link the public repository, deployed app and sponsor evidence.

☐  Check the current submission rules and video limits before upload.

## Sponsor reference links

Hedera prize requirements
https://ethglobal.com/events/ethonline2026/prizes/hedera

The Graph prize requirements
https://ethglobal.com/events/ethonline2026/prizes/the-graph

## First team session

Aditya starts the live indexing feasibility check. Kavish starts the controlled Blocky402 payment proof. The lead commits interfaces, fixtures and the mock workflow skeleton. All three review the same event schema before separating into their workstreams.